## Sheet0
CR Text | CR ID | ASIL Level | acceptance LG against LuK requirement | planned implementation milestone/date | implementation state | if test: Test ID | verification method | test case review status | test result['1495334', ' 1495339'] | verification status | SysRS ID | SwRS ID | If NOK or test not possible, add rational and write action planned
All workproducts related to requirements rated with ASIL > QM shall be provided to the corresponding SW TPL and FSM. | B-SW_2478 |  | accepted |  | implemented | SysTS_CheckList_035 | Requirement-based test | reviewed | NT | not finished | SysConstraints_384
The supplier shall provide arguments of the proper strategy used and evidences for the achievement of all safety requirements.(e.g.: mechanisms to ensure proper writing/reading of the EEPROM datas) | B-SW_2479 |  | accepted |  | implemented | SysTS_CheckList_001 | Requirement-based test | reviewed | NT | not finished | SysConstraints_017
[CARB OBD II 1968.2] OBD II regulation, §1968.2. Malfunction and Diagnostic System Requirements--2004 and Subsequent Model-Year Passenger Cars, Light-Duty Trucks, and Medium-Duty Vehicles and Engines. | B-SW_916 |  | accepted |  | implemented | SysTS_CheckList_003 | Requirement-based test | reviewed | NT | not finished | SysConstraints_226
[CARB OBD II 1968.5] OBD II regulation, § 1968.5. Enforcement of Malfunction and Diagnostic System Requirements for 2004 and Subsequent Model-Year Passenger Cars, Light-Duty Trucks, and Medium-Duty Vehicles and Engines. | B-SW_917 |  | accepted |  | implemented | SysTS_CheckList_004 | Requirement-based test | reviewed | NT | not finished | SysConstraints_227
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | n/a | n/a | n/a | NT | not finished | SysNFR_353
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | n/a | n/a | n/a | NT | not finished | SysNFR_353
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | SysTS_QE_252 | Non-functional | reviewed | NT | not finished | SysNFR_353
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | SysTS_QE_253 | Non-functional | reviewed | NT | not finished | SysNFR_353
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | SysTS_QE_372 | Non-functional | reviewed | NT | not finished | SysNFR_353
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | B-SW_794 |  | accepted | M10 (29.06.2018) | implemented | SwTS_TC_350 | requirement based test | reviewed | Passed(session : 1495339) | finished |  | Swnf_063
The BSW shall provide all data that can be changed / accessed by the UDS Services ReadDataByIdentifier 0x22 and WriteDataByIdentifier 0x2E as XCP measurement values in the A2L file. | B-SW_2338 |  | accepted |  | implemented | n/a | n/a | n/a | NT | not finished | SysFR_083
The BSW shall provide all data that can be changed / accessed by the UDS Services ReadDataByIdentifier 0x22 and WriteDataByIdentifier 0x2E as XCP measurement values in the A2L file. | B-SW_2338 |  | accepted |  | implemented | n/a | n/a | n/a | NT | not finished |  | Swf_470
The values of the calibration parameters for the FMM shall be defined by LuK for all the BSW and ASW failure detections. | B-SW_3338 |  | accepted with deviation | M11 (02.11.2018) | implemented | n/a | n/a | n/a | NT | not finished | SysFR_015
The values of the calibration parameters for the FMM shall be defined by LuK for all the BSW and ASW failure detections. | B-SW_3338 |  | accepted with deviation | M11 (02.11.2018) | implemented | n/a | n/a | n/a | NT | not finished |  | Swf_008
The values of the calibration parameters for the FMM shall be defined by LuK for all the BSW and ASW failure detections. | B-SW_3338 |  | accepted with deviation | M11 (02.11.2018) | implemented | SwTS_Diag_997 | requirement based test | reviewed | NT | not finished |  | Swf_008