## Sheet0
CR Text | CR ID | ASIL Level | acceptance LG against LuK requirement | implementation state | planned implementation milestone/date | verification method | if test: Test ID | test case review status | verification status | test result['1495334', ' 1495339'] | If NOK or test not possible, add rational and write action planned | SysRS ID | SwRS ID
All workproducts related to requirements rated with ASIL > QM shall be provided to the corresponding SW TPL and FSM. | ['B-SW_2478'] | None | accepted | implemented | n/a | Requirement-based test | SysTS_CheckList_035 | reviewed | not finished | NT |  | SysConstraints_384
The supplier shall provide arguments of the proper strategy used and evidences for the achievement of all safety requirements.(e.g.: mechanisms to ensure proper writing/reading of the EEPROM datas) | ['B-SW_2479'] | None | accepted | implemented | n/a | Requirement-based test | SysTS_CheckList_001 | reviewed | not finished | NT |  | SysConstraints_017
[CARB OBD II 1968.2] OBD II regulation, ¡×1968.2. Malfunction and Diagnostic System Requirements--2004 and Subsequent Model-Year Passenger Cars, Light-Duty Trucks, and Medium-Duty Vehicles and Engines. | ['B-SW_916'] | None | accepted | implemented | n/a | Requirement-based test | SysTS_CheckList_003 | reviewed | not finished | NT |  | SysConstraints_226
[CARB OBD II 1968.5] OBD II regulation, ¡× 1968.5. Enforcement of Malfunction and Diagnostic System Requirements for 2004 and Subsequent Model-Year Passenger Cars, Light-Duty Trucks, and Medium-Duty Vehicles and Engines. | ['B-SW_917'] | None | accepted | implemented | n/a | Requirement-based test | SysTS_CheckList_004 | reviewed | not finished | NT |  | SysConstraints_227
The initialisation task delay of the Basic SW(Ignition on to cyclic tasks running) shall not exceed 150ms. | ['B-SW_794'] | None | accepted | implemented | M10 (29.06.2018) | Requirement-based test | SysTS_QE_105 | reviewed | not finished | NT |  | SysNFR_353
[6 empty] | Requirement-based test | SysTS_QE_104 | reviewed | not finished | NT
[6 empty] | Non-functional | SysTS_QE_252 | reviewed | not finished | NT
[6 empty] | Non-functional | SysTS_QE_253 | reviewed | not finished | NT
[6 empty] | Non-functional | SysTS_QE_372 | reviewed | not finished | NT
[6 empty] | requirement based test | SwTS_TC_350 | reviewed | finished | Passed(session : 1495339) |  |  | Swnf_063
The BSW shall provide all data that can be changed / accessed by the UDS Services ReadDataByIdentifier 0x22 and WriteDataByIdentifier 0x2E as XCP measurement values in the A2L file. | ['B-SW_2338'] | None | accepted | implemented | n/a | requirement based test | SwTS_Check_052 | reviewed | not finished | Skipped(session : 1495339) |  | SysFR_083
[6 empty] | requirement based test | SwTS_Check_052 | reviewed | not finished | Skipped(session : 1495339) |  |  | Swf_470
The values of the calibration parameters for the FMM shall be defined by LuK for all the BSW and ASW failure detections. | ['B-SW_3338'] | None | accepted with deviation | implemented | M11 (02.11.2018) | requirement based test | SwTS_TC_453 | reviewed | not finished | NT |  | SysFR_015
[6 empty] | requirement based test | SwTS_TC_453 | reviewed | not finished | NT |  |  | Swf_008
[6 empty] | requirement based test | SwTS_Diag_997 | reviewed | not finished | NT